## Project Schedule
PROJECT SCHEDULE TEMPLATE
PROJECT NAME | PROJECT MANAGER
Golf Analytics Platform | Thomas Kulch
START DATE | END DATE | OVERALL PROGRESS
2025-06-04 | 2025-08-04 | 75%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Come up with Project Idea | Thomas | 2025-06-04 | 2025-06-04 | 1 | Complete
Submit Iteration 2 | Thomas | 2025-06-05 | 2025-06-05 | 1 | Complete | Pivoted from Golf course manager with DB management to big data platform with simple ML models
Submit Iteration 3 | Thomas | 2025-06-05 | 2025-06-05 | 1 | Complete
explore data | Thomas | 2025-07-08 | 2025-07-09 | 2 | Complete | all steps outlined in document if we need a reference
data reshaping | Thomas | 2025-07-08 | 2025-07-09 | 2 | Complete
statistical analysis | Thomas | 2025-07-10 | 2025-07-10 | 1 | Complete
database design | Thomas | 2025-07-10 | 2025-07-11 | 2 | Complete
handicap update calculator | Thomas | 2025-07-16 | 2025-07-16 | 1 | Complete | put this as a trigger in SQL for after insert of records
pyspark pipeline | Thomas | 2025-07-11 | 2025-07-18 | 7 | Complete | one of the bulkiest bits of the project, we are at trying to insert data, code is pretty much written for pipeline
feature engineering | Thomas | 2025-07-18 | 2025-07-20 | 3 | Complete | pulled from db. Ready for ml
ML model 1 : Score prediction | Thomas | 2025-07-21 | 2025-07-23 | 3 | Complete | Did dynamic pricing func here too
Export model for use in program | Thomas | 2025-07-24 | 2025-07-25 | 2 | Complete | Learn how to deploy these models to be used by our program after they've been trained
Program for booking rounds and entering rounds | Thomas | 2025-07-26 | 2025-07-29 | 4 | In Progress
testing files or make flask app | Thomas | 2025-07-30 | 2025-07-30 | 1 | Not Started | do test files if we are limited on time
clean up code/push to git | Thomas | 2025-07-31 | 2025-08-01 | 2 | Not Started
create report and presentation slides | Thomas | 2025-08-02 | 2025-08-04 | 3 | Not Started

## Template
PROJECT SCHEDULE TEMPLATE
PROJECT NAME | PROJECT MANAGER
PROJECT DELIVERABLE
SCOPE STATEMENT
START DATE | END DATE | OVERALL PROGRESS
2025-06-05 | 2025-08-15 | 0%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Set Kickoff Meeting | Alex B. | 2025-01-08 | 2025-01-08 | 2 | Complete
Agree on Objectives | Frank C. | 2025-09-03 | 2025-09-07 | 5 | Complete
Detailed Requirements | Jacob S. | 09/07 | 09/12 | 6 | Complete
Hardware Requirements | Jacob S. | 09/09 | 09/11 | 3 | Overdue
Final Resource Plan | Jacob S. | 09/11 | 09/15 | 5 | In Progress
Staffing | Alex B. | 09/16 | 09/17 | 2 | In Progress
Technical Requirements | Frank C. | 09/17 | 09/21 | 5 | Not Started
DB Development | Shari W. | 09/22 | 09/24 | 3 | Not Started
API Development | Shari W. | 09/23 | 09/27 | 5 | Not Started
UI Client | Alex B. | 09/25 | 09/29 | 5 | Not Started
Testing | Kennedy K. | 09/24 | 10/02 | 9 | Not Started
Development Complete | Jacob S. | 10/02 | 10/05 | 4 | Not Started
Hardware Configuration | Alex B. | 10/05 | 10/07 | 3 | Not Started
System Testing | Kennedy K. | 10/06 | 10/09 | 4 | Not Started